## Assumptions
WBS Cost Model — Assumptions & Rate Card
Blue cells = inputs you can change ¦ Black cells = calculated ¦ All costs in USD
RATE CARD
Role | Onshore ($/hr) | Offshore ($/hr) | Onshore ($/pd) | Offshore ($/pd) | Notes
Engagement Director | 195 | — | 1560 | — | Onshore only
Solution Architect | 175 | 68 | 1400 | 544
Senior Data/ML Engineer | 145 | 52 | 1160 | 416 | Databricks certified
Data/Analytics Engineer | 115 | 38 | 920 | 304
DataOps/Platform Engineer | 125 | 42 | 1000 | 336
BA / Governance Lead | 95 | 30 | 760 | 240
QA / Data Steward | 85 | 25 | 680 | 200
DELIVERY MODEL
Offshore ratio | 83%
Onshore ratio | 17%
Working days per month | 21
Hours per day | 8
Coordination buffer % | 5%
BLENDED RATE CALCULATION
Avg onshore rate ($/hr) | 133.5714
Avg offshore rate ($/hr) | 42.5
Avg onshore rate ($/pd) | 1068.5714
Avg offshore rate ($/pd) | 340
BLENDED RATE ($/hr) | 57.9821
BLENDED RATE ($/pd) | 463.8571
PHASE PARAMETERS
Parameter | Phase 1 | Phase 2 | Phase 3 | Total
Duration (months) | 4 | 6 | 6 | 16
Onshore FTE (peak) | 5 | 4 | 4 | 13
Offshore FTE (peak) | 13 | 18 | 14 | 45
Total FTE (peak) | 18 | 22 | 18 | 22
Effort — deliverables (pd) | 2100 | 2900 | 2300 | 7300
Coordination buffer (5%) (pd) | 105 | 145 | 115 | 365
TOTAL EFFORT (incl. buffer) (pd) | 2205 | 3045 | 2415 | 7665
PHASE COST ($) | 1022805 | 1412445 | 1120215 | 3555465

## WBS Detail
Work Breakdown Structure - Detailed Cost Model
Blue = inputs ¦ Black = formulas ¦ Costs = Effort (pd) × Blended Rate from Assumptions sheet
WBS ID | Deliverable / Work Package | Phase | Lead Role | Offshore Ratio | Effort (pd) | Onshore pd | Offshore pd | Cost ($) @ blended rate | Notes
1.0 | Platform & Infrastructure | 1 | Cloud Architect | 70% | 700 | 210 | 490 | 324700 | AWS foundation + IaC baseline
1.1 | AWS VPC, IAM, Direct Connect, Security Groups | 1 | Cloud Architect | 60% | 80 | 32 | 48 | 37108.5714 | On-prem to cloud connectivity
1.2 | Databricks Workspace + Unity Catalog setup | 1 | Platform Lead | 80% | 120 | 24 | 96 | 55662.8571 | Cluster config, UC admin, workspace isolation
1.3 | Terraform IaC + CI/CD baseline (DEV→SIT→UAT→PROD) | 1 | DataOps Engineer | 85% | 80 | 12 | 68 | 37108.5714 | Infra as code, pipeline templates
1.4 | Security hardening - AWS WAF, GuardDuty, CloudTrail | 1 | Cloud Architect | 80% | 80 | 16 | 64 | 37108.5714 | Security posture, VPC flow logs, audit trail
1.5 | Multi-region HA - Active-Active across 2 AWS regions | 1 | Platform Lead | 75% | 120 | 30 | 90 | 55662.8571 | S3 CRR, Databricks multi-region workspace config
1.6 | Monitoring & alerting - Databricks Lakehouse Monitoring | 1 | DataOps Engineer | 85% | 80 | 12 | 68 | 37108.5714 | Pipeline health, DQ drift, SLA alerting
1.7 | Performance baseline testing & cluster tuning | 1 | Platform Lead | 80% | 80 | 16 | 64 | 37108.5714 | Photon tuning, cluster policies, auto-scaling validation
1.8 | Environment management (DEV / SIT / UAT / PROD) | 1 | DataOps Engineer | 85% | 60 | 9 | 51 | 27831.4286 | Workspace-per-env, feature branch CI/CD
2.0 | Data Ingestion & Migration | 1-2 | Sr Data Engineer | 85% | 920 | 138 | 782 | 426748.5714 | CDC + historical + streaming
2.1 | SAP HANA + MDM CDC pipelines (AWS DMS) | 1 | Sr Data Engineer | 85% | 180 | 27 | 153 | 83494.2857 | Full + incremental extract via DMS
2.2 | Historical data load - ~5 years backfill | 1 | Data Engineer | 90% | 200 | 20 | 180 | 92771.4286 | Auto Loader batch ingest to Bronze
2.3 | Streaming pipelines - Kinesis + DLT | 2 | Sr Data Engineer | 85% | 180 | 27 | 153 | 83494.2857 | Real-time event ingest <500ms
2.4 | Data profiling & source system analysis sprint | 1 | Sr Data Engineer | 85% | 120 | 18 | 102 | 55662.8571 | Schema discovery, volume analysis, DQ baseline
2.5 | MDM system integration + master data pipelines | 1 | Sr Data Engineer | 85% | 120 | 18 | 102 | 55662.8571 | Product, customer, supplier master data CDC
2.6 | Data quality gate implementation (DLT Expectations) | 2 | Sr Data Engineer | 85% | 120 | 18 | 102 | 55662.8571 | Warn/drop/fail rules across all ingestion pipelines
3.0 | Medallion Lakehouse (Bronze → Silver → Gold) | 1-2 | Data Engineer | 85% | 1160 | 174 | 986 | 538074.2857 | Core Delta Lake zones
3.1 | Bronze zone - raw ingestion layer | 1 | Data Engineer | 90% | 120 | 12 | 108 | 55662.8571 | Schema enforcement, DLT Expectations
3.2 | Silver zone - cleanse, conform, deduplicate | 1-2 | Data Engineer | 85% | 200 | 30 | 170 | 92771.4286 | DQ rules, SCD2, cross-source joins
3.3 | Gold zone - 6 domain data products | 2 | Data Engineer + BA | 80% | 200 | 40 | 160 | 92771.4286 | Supply Chain, Brand, Consumer, Margin, Home Care, Beauty
3.4 | Delta Live Tables pipeline orchestration (all zones) | 1-2 | Data Engineer | 85% | 160 | 24 | 136 | 74217.1429 | Full DLT DAG design, dependency mgmt, retry logic
3.5 | Data partitioning, Z-ordering & performance optimisation | 2 | Data Engineer | 85% | 120 | 18 | 102 | 55662.8571 | Partition strategy per domain, vacuum, OPTIMIZE jobs
3.6 | Schema registry & schema evolution management | 1-2 | Data Engineer | 85% | 100 | 15 | 85 | 46385.7143 | Schema versioning, backward compat, auto-schema inference
3.7 | Time travel, CDC merge patterns & SCD2 implementation | 2 | Data Engineer | 85% | 120 | 18 | 102 | 55662.8571 | MERGE INTO, SCD2 for slowly changing dimensions
3.8 | Data lineage mapping across all 6 domain products | 2 | Governance Lead | 70% | 140 | 42 | 98 | 64940 | Unity Catalog lineage, column-level impact analysis
4.0 | Analytics, BI & ML Platform | 2-3 | Analytics + ML Pod | 80% | 1740 | 348 | 1392 | 807111.4286 | Full analytics + ML stack
4.1 | BI connectivity + semantic layer (Power BI / Tableau) | 2 | BI Developer | 85% | 240 | 36 | 204 | 111325.7143 | Direct Lake mode, certified datasets
4.2 | Supply chain analytics - 5 use cases | 2 | Analyst + Data Scientist | 80% | 280 | 56 | 224 | 129880 | Demand, inventory, supplier, logistics, margin
4.3 | ML platform - MLflow + Feature Store + Model Serving | 3 | ML Engineer | 80% | 300 | 60 | 240 | 139157.1429 | Training pipelines, registry, deployment
4.4 | Demand forecasting + margin analytics models | 3 | Data Scientist | 80% | 160 | 32 | 128 | 74217.1429 | Phase 3 ML models in production
4.5 | e-Influence analytics domain - data product design & build | 3 | Data Scientist | 80% | 200 | 40 | 160 | 92771.4286 | Digital signal to shelf offtake attribution model
4.6 | Self-serve SQL layer - certified dataset publishing | 2 | BI Developer | 85% | 120 | 18 | 102 | 55662.8571 | Power BI Direct Lake, certified dataset governance
4.7 | ML Feature Store setup + feature engineering pipelines | 3 | ML Engineer | 80% | 160 | 32 | 128 | 74217.1429 | Feature definitions, versioning, online/offline serving
4.8 | Model monitoring & drift detection - production MLOps | 3 | ML Engineer | 80% | 120 | 24 | 96 | 55662.8571 | Lakehouse Monitoring, retraining triggers
4.9 | Dashboard UAT, sign-off & hypercare (all BI workstreams) | 2-3 | BI Developer | 80% | 160 | 32 | 128 | 74217.1429 | Client UAT support, defect resolution, go-live prep
5.0 | Governance, Security & Compliance | 1-3 | Governance Lead | 75% | 900 | 225 | 675 | 417471.4286 | Unity Catalog + multi-region compliance
5.1 | Unity Catalog RBAC, masking, tagging setup | 1 | Governance Lead | 70% | 160 | 48 | 112 | 74217.1429 | Row/column policies, PII tags, lineage
5.2 | Data Steward programme - onboarding + certification | 2 | BA / Governance Lead | 80% | 160 | 32 | 128 | 74217.1429 | Data Steward roles, glossary, ownership
5.3 | Compliance framework - GDPR, CCPA, PDPA, PIPL, LGPD | 2-3 | Governance Lead | 75% | 160 | 40 | 120 | 74217.1429 | Regional workspace isolation, audit logs
5.4 | Data classification & sensitivity tagging (all domains) | 1-2 | Governance Lead | 75% | 120 | 30 | 90 | 55662.8571 | PII, confidential, public tags via Unity Catalog
5.5 | Data product SLA & chargeback instrumentation | 2 | DataOps Engineer | 80% | 120 | 24 | 96 | 55662.8571 | DBU metering per BU, S3 cost allocation tagging
5.6 | Audit logging, access reviews & compliance reporting | 2-3 | Governance Lead | 75% | 100 | 25 | 75 | 46385.7143 | Monthly access reports, GDPR audit trail
5.7 | Data Mesh operating model documentation & playbooks | 2 | BA / Governance Lead | 80% | 80 | 16 | 64 | 37108.5714 | Domain ownership, data product contracts, RACI
6.0 | Quick Win - Supply Chain KPI Dashboard | 1 | BI Developer + DE | 80% | 200 | 40 | 160 | 92771.4286 | Month 3 delivery target
6.1 | Supply Chain domain Bronze + Silver ingest | 1 | Data Engineer | 90% | 80 | 8 | 72 | 37108.5714 | 2 source systems, DLT pipeline
6.2 | Demand domain Bronze + Silver ingest | 1 | Data Engineer | 90% | 60 | 6 | 54 | 27831.4286 | Forecast inputs, historical demand
6.3 | Power BI KPI dashboard - 5 report packs | 1 | BI Developer | 80% | 60 | 12 | 48 | 27831.4286 | Replaces 5 manual weekly Excel reports
7.0 | Capability Building | 1-3 | BA / Governance Lead | 80% | 500 | 100 | 400 | 231928.5714 | Embedded training workstream
7.1 | Self-serve SQL bootcamp - brand managers | 2 | BA / Governance Lead | 80% | 80 | 16 | 64 | 37108.5714 | SQL basics, Databricks SQL UI, certified datasets
7.2 | Data Steward certification programme | 2 | BA / Governance Lead | 80% | 80 | 16 | 64 | 37108.5714 | Governance tools, ownership, quality gates
7.3 | ML literacy programme - analytics teams | 3 | BA / Governance Lead | 80% | 80 | 16 | 64 | 37108.5714 | AutoML, feature engineering, model consumption
7.4 | Centre of Excellence handover + documentation | 3 | BA / Governance Lead | 80% | 60 | 12 | 48 | 27831.4286 | Runbooks, standards, CoE governance model
7.5 | Change management & stakeholder comms programme | 1-3 | BA / Governance Lead | 60% | 120 | 48 | 72 | 55662.8571 | Comms plan, exec updates, user adoption tracking
7.6 | Data literacy baseline assessment & gap analysis | 1 | BA / Governance Lead | 70% | 80 | 24 | 56 | 37108.5714 | Skills assessment across 3 divisions, training roadmap
8.0 | KT, Hypercare & Runbooks | 3 | All Leads | 70% | 400 | 120 | 280 | 185542.8571 | End-of-programme handover
8.1 | Knowledge transfer sessions (all workstreams) | 3 | All Leads | 70% | 80 | 24 | 56 | 37108.5714 | Structured KT workshops with client team
8.2 | Runbook + operational documentation | 3 | DataOps Engineer | 80% | 40 | 8 | 32 | 18554.2857 | Platform ops, incident playbooks
8.3 | Hypercare support - first 30 days post go-live | 3 | All Leads | 65% | 40 | 14 | 26 | 18554.2857 | Triage, bug fixes, performance tuning
8.4 | Platform operations handover - runbooks & SOP library | 3 | DataOps Engineer | 80% | 80 | 16 | 64 | 37108.5714 | Incident playbooks, on-call procedures, SLA mgmt
8.5 | Production support - 60-day hypercare window | 3 | All Leads | 65% | 100 | 35 | 65 | 46385.7143 | L2/L3 support, performance tuning, user queries
8.6 | Post-implementation review & optimisation recommendations | 3 | Solution Architect | 50% | 60 | 30 | 30 | 27831.4286 | PIR report, Phase 4 roadmap recommendations
WBS TOTAL | All 53 deliverable work packages |  |  | 79.58% | 6520 | 1355 | 5165 | 3024348.5714 | excl. overhead & buffer
PROGRAMME COST RECONCILIATION - How WBS cost builds to total programme cost
Component | Person-days | Rate ($/pd) | Cost ($) | [5 empty] | Explanation
WBS deliverable effort | 6520 | 463.8571 | 3024348.5714 | [5 empty] | 53 defined work packages - full deliverable scope
Programme overhead | 780 | 463.8571 | 361808.5714 | [5 empty] | Agile ceremonies, code reviews, deployment, team management (12.0% of deliverables - industry standard 10-15%)
Coordination buffer (5%) | 365 | 463.8571 | 169307.8571 | [5 empty] | 5% buffer on total deliverable + overhead effort
TOTAL PROGRAMME COST | 7665 | 463.8571 | 3555465 | [5 empty] | Phase Summary total ¦ Blended $464/pd ¦ 83% offshore / 17% onshore

## Phase Summary
Phase Cost & Effort Summary
All values flow from WBS Detail and Assumptions sheets
Metric | Phase 1 | Phase 2 | Phase 3 | Buffer | Total | Notes
Duration (months) | 4 | 6 | 6
Peak FTE (total) | 18 | 22 | 18
Effort - deliverables (pd) | 2100 | 2900 | 2300 | 365 | 7300
Coordination buffer (pd) | 105 | 145 | 115 |  | 365
Total effort incl. buffer (pd) | 2205 | 3045 | 2415 | 365 | 7665
Phase cost ($) | 1022805 | 1412445 | 1120215 | 365 | 3555465
Engagement model: Phase 1 = Fixed Price ¦ Phase 2 = T&M ¦ Phase 3 = T&M ¦ Blended rate = 80% offshore / 20% onshore at $58/hr ($464/pd)